## Overview
DESKTOP MESSENGER — PROJECT MANAGEMENT
Submission reconstruction plan • not a verified historical task log
Project | Desktop Messenger | Completed tasks | 19
Version concept | DesktopMessengerPythonSyncedLively | Total tasks | 24
Course | Systems Analysis and Design / تحليل وتصميم النظم | Completion | 79.17%
Students | يوسف عبدالسلام • علي المختار | High risks (score ≥ 15) | 6
Supervisor | الدكتور بلال الميتمي
University | Al Jeel Al Jadeed University
Evidence note: responsibilities are a balanced academic model, not verified historical evidence. Core tests passed; Windows UI, native executable, and two-device acceptance remain explicit gates.

## Work Breakdown
ID | Area | Task | Owner | Deliverable / gate | Status
WBS-01 | Requirements | Confirm scope, modes, ports and evidence limits | Joint | Requirements baseline | Complete
WBS-02 | Reference audit | Inventory 1,483 physical files and inspect contents | Ali | Audit inventory | Complete
WBS-03 | Architecture | Define layered PySide6/SQLite/network/sync design | Joint | Architecture model | Complete
WBS-04 | Database | Create UUID-based SQLite schema and indexes | Yousef | SQL + SQLite database | Complete
WBS-05 | Security | Implement scrypt, X25519, HKDF and AES-GCM helpers | Ali | Security modules | Complete
WBS-06 | Networking | Implement bounded LAN protocol and port 8765 service | Ali | LAN modules | Complete
WBS-07 | Networking | Implement port 9876 demonstration relay | Ali | Relay modules | Complete
WBS-08 | Synchronization | Implement pending export, acknowledgement and idempotent apply | Joint | Sync engine | Complete
WBS-09 | Desktop UI | Create dark navigation shell and feature pages | Yousef | PySide6 source | Complete
WBS-10 | Desktop UI | Wire UI actions to network/sync controllers | Joint | Integrated UI | Pending
WBS-11 | Mobile | Create source-only Flutter companion structure | Yousef | Flutter source | Complete
WBS-12 | UML | Create use case, activity, sequence, state and class views | Yousef | UML PNG/SVG/draw.io | Complete
WBS-13 | DFD | Create context, Level 0, three Level 1 views and dictionary | Yousef | DFD package | Complete
WBS-14 | Database design | Create conceptual ER_D and physical ERD | Yousef | ERD package | Complete
WBS-15 | Documentation | Create academic report and applied lab archive | Joint | DOCX/PDF/labs.zip | Complete
WBS-16 | Core QA | Compile Python and execute nine unit tests | Joint | Test log | Complete
WBS-17 | Artifact QA | Render documents, diagrams and spreadsheets | Yousef | Visual QA evidence | Complete
WBS-18 | Database QA | Run integrity and foreign-key checks | Yousef | Validated SQLite file | Complete
WBS-19 | Windows build | Build PyInstaller distribution on Windows | Ali | DesktopMessenger dist | Pending
WBS-20 | LAN acceptance | Test two laptops over hotspot and reconnect | Joint | Signed test record | Pending
WBS-21 | Relay acceptance | Test reachable non-loopback relay | Ali | Signed test record | Pending
WBS-22 | Security hardening | Add TLS and peer identity verification | Joint | Hardened protocol | Future
WBS-23 | Final audit | Scan domain contamination and validate archive | Joint | Verification matrix | Complete
WBS-24 | Submission | Create final ZIP and record checksum | Ali | Final archive | Complete

## Responsibility
RESPONSIBILITY MODEL
Reasonable balanced model • replace if verified historical allocation is supplied
Workstream | Ali — علي المختار | Yousef — يوسف عبدالسلام | Joint | Rationale | Evidence status
Requirements & coordination | Lead | Support | Approve | Align scope and submission | Proposed
Database & data flows | Review | Lead | Approve | Schema and ERD/DFD continuity | Proposed
UI/UX | Review | Lead | Integrate | Desktop interaction and visual evidence | Proposed
LAN & relay | Lead | Support | Integrate | Connectivity implementation | Proposed
Synchronization | Integrate | Support | Lead | Cross-cutting data consistency | Proposed
Security | Review | Support | Validate | Cryptographic and transport controls | Proposed
Testing | Network/reconnect | Functional/data | Regression | Evidence by test type | Proposed
Documentation | Management/deployment | Technical/diagrams | Final review | Balanced submission effort | Proposed
Presentation | Prepare | Prepare | Deliver | Joint academic ownership | Proposed

## Risk Register
ID | Risk / limitation | Owner | Likelihood (1–5) | Impact (1–5) | Score | Mitigation / next action | Status
R-01 | No supplied final Desktop Messenger source | Joint | 5 | 5 | 25 | Treat reconstruction as baseline and compare if source is supplied | Open
R-02 | PySide6 UI not launched in generation environment | Yousef | 4 | 4 | 16 | Run native Windows smoke test | Open
R-03 | UI network buttons are not wired | Joint | 5 | 4 | 20 | Integrate controller/async worker | Open
R-04 | Relay transport lacks TLS | Ali | 5 | 5 | 25 | Add authenticated TLS before public use | Open
R-05 | Synchronization supports only selected operations | Joint | 4 | 5 | 20 | Add versioned handlers and per-entity conflict rules | Open
R-06 | Hotspot client isolation | Ali | 3 | 4 | 12 | Verify peer routing and firewall before demonstration | Open
R-07 | No native Windows executable | Ali | 4 | 4 | 16 | Build and validate with included PyInstaller specification | Open
R-08 | Attachment transfer not end-to-end validated | Yousef | 3 | 4 | 12 | Add encrypted streaming and integrity tests | Open
R-09 | Clock skew affects timestamp conflict comparison | Joint | 3 | 3 | 9 | Prefer versions/vector metadata for shared updates | Open

## Test Matrix
ID | Area | Test objective | Type | Execution | Result | Evidence / limitation
T-01 | Password hashing | Hash/verify and wrong-password rejection | Automated unit | Executed | PASS | tests/test_crypto.py
T-02 | Private key protection | Wrap/recover X25519 private key | Automated unit | Executed | PASS | tests/test_crypto.py
T-03 | Message cryptography | X25519/HKDF/AES-GCM round trip | Automated unit | Executed | PASS | tests/test_crypto.py
T-04 | User authentication | Create and authenticate account | Automated unit | Executed | PASS | tests/test_database.py
T-05 | Friend/direct chat | Accept request and stable chat UUID | Automated unit | Executed | PASS | tests/test_database.py
T-06 | Protocol frame | Encode/decode bounded JSON frame | Automated unit | Executed | PASS | tests/test_protocol.py
T-07 | Relay proof | Challenge/response proof | Automated unit | Executed | PASS | tests/test_protocol.py
T-08 | SQLite schema | Initialize and enable foreign keys | Automated unit | Executed | PASS | tests/test_schema.py
T-09 | Sync idempotency | Same operation applied once | Automated unit | Executed | PASS | tests/test_sync.py
T-10 | PySide6 UI | Launch, navigate, register and login | Windows smoke | Not executed | PENDING | PySide6 unavailable here
T-11 | LAN/hotspot | Two laptops on shared hotspot, port 8765 | Acceptance | Not executed | PENDING | Requires two Windows computers
T-12 | Internet relay | Reachable non-loopback relay, port 9876 | Acceptance | Not executed | PENDING | Requires reachable relay host
T-13 | Reconnect/retry | Pending operation automatically retries | Integration | Not executed | PENDING | Controller/scheduler integration required
T-14 | Windows build | PyInstaller distribution on clean machine | Deployment | Not executed | PENDING | Use Published/build_windows.bat